## General Schedule
Página | Componentes | Funcion Especifica de Consulta | Time (Days) |  | Requirements
|  |  | FrontEnd | BackEnd
Lobby | Contest Promotions | getContests | 10 | 0 | Already Done
| Active Contests | getPromotions | 10 | 2
| Informations | getInformations/getInformations(StartDate,EndDate) | TBD* | 1
| Next Context Timer | getNextContestTime(IEnumerable<Contest>) | 2 | 2
| Contest Filters | getContests(Acoording to filters) | 3 | 1
| Menus |  | 2 | 0
Home | Promotions List | getPromotions | TBD* | 0 | Backend Already Done for the Lobby Page
| Notification List | getNotifications |  | 1
| Basic Site Information | TBD |  | TBD | * when desing is finished
Registration Form |  | putUser(userInfo) | TBD* | 7 | * when desing is finished - fe time extended to study REST
Login form |  |  | TBD* | 3 | * when desing is finished
My Account | User Info | getUserInfo(username) | TDB* | 0.5 | * when desing is finished
Points
Money
Stats | Earned Cash | getUserEarnedCash(actualUser) | TBD* | 0.5 | * when desing is finished - fe time subject to definition of prizing
| Graphics | TBD |  | TBD
| Best Rivals (off Friends List) | getUsersBestRivals(actualUser, IEnumerable<User>, amount) |  | 0.5
| Worst Rivals (off Friends List) | getUsersWorstRivals(actualUser, IEnumerable<User>, amount) |  | 0.5
| More To Be Determined | TBD |  | TBD
Friends | Friends List | getUserFrieds(actualUser) | TBD* | 3
Add Funds | Payment Platform Fields* | TBD | TBD* | TBD
Notifications | Notification List | getNotifications | TBD* | 0 | * when desing is finished -- Already done in Lobby
History | List of Lineups | getLineups(actualUser) | TBD* | 5 | * when desing is finished
| Winnings (Total) | getTotalWinnings(actualUser) |  | 5
| Record (W/L) | getWinLoseRecord(actualUser) |  | 2
Help | Help Topics | TDB | TBD* | TBD | We need to discuss help topics and how to show them - * when desing is finished
Partake Contest | Contest Info | getContest(Id) | 1 | 2
| Games | getGamesFromContest(contestID) | 1 | 2
| Teams of The Games | getTeamsFromGames(IEnumerable<Game>) | 3 | 0 | Uses getTeamsFromGame
|  | getTeamsFromGame(GameID) |  | 2
| Players of The Teams | getPlayersFromTeam(TeamID) | 3 | 0 | Already done
|  | getPlayersFromTeams(IEnumerable<Teams>) |  | 1 | Uses getPlayersFromTeam
| Lineup | putLineup(Lineup) | 5 | 10 | Requires to study a bit of REST and to test the saving modality on the db
View Contest | Contest Info | getContest(Id) | 7 | 0 | Defined in Partake Contests
Live Contest | Contest Info | getContest(Id) | 1 | 0 | Defined in Partake Contests
| Lineup | getLineups(actualUser) | 1 | 2
| Competitors Lineup | getLineups(IdContest) | 1 | 2
| Points/Goals | getGoals(ContestID) | 2 | 5
|  | getObtainedPoints(ContestID) | 3 | 5
My Upcoming Contest | List of Contest ordered by lineup | getContests(Date) | TBD* | 2
Create Contest | Contest Gral Info | getContest(Id) | TBD* | 0 | Defined in Partake Contests
| Prize Structure(Depend ^, ^^) | TBD |  | TBD | funtions That depend on the Contest Type and Entry Fee TBD
Player | Player Info | getPlayer(ID) | TBD* | 2
| Game Stats (TBD) | TBD |  | TBD
| Player Stats (TBD) | TBD
| Recent Performance (TBD) | TBD
| News (Related) | getNews(Player) |  | 3
Team | Team Info | getTeam(ID) | TBD* | 2
| News (Related) | getNews(Team) |  | 2
| Upcoming Games | getGamesfromTeam(IdTeam) |  | 2
Game | Game Info | getGame(IDGame) | TBD* | 2
Lineup | List of Players | getPlayers(lineupID) | TBD* | 2
|  | Weeks in Case of Implementation Errors | 4 | 4
|  | Days | 59 | 86
|  | Weeks | 8.4286 | 12.2857

## Backend Schedule
Function | API Layer Implementation | Time(Days) | Date |  | Time(Days) | Date |  | Completed
|  | Implentation | Start | End | Testing | Start | End | (%)
getContests | DataAccess | [6 empty] | 100%
Domain
Service
Dto
getActiveContests | DataAccess | 1 | 2018-01-21 | 2018-01-21 | 1 | 2018-01-21 | 2018-01-21
Domain
Service
Dto
getActiveNotifications | DataAccess | 1 | 2018-01-18 | 2017-01-18 | 1 | 2018-01-18 | 2018-01-18 | 25%
Domain
Service
Dto
getUserActiveNotifications(user) | DataAccess | 1 | 2018-01-18 | 2017-01-18 | 1 | 2018-01-18 | 2018-01-18 | 25%
Domain
Service
Dto
getInformations | DataAccess | 1 | 2018-01-18 | 2017-01-18 | 1 | 2018-01-18 | 2018-01-18 | 25%
Domain
Service
Dto
getInformations(Start Date, End Date) | DataAccess | 1 | 2018-01-18 | 2017-01-18 | 1 | 2018-01-18 | 2018-01-18 | 25%
Domain
Service
Dto
getPromotions | DataAccess | 1 | 2018-01-19 | 2018-01-19 | 1 | 2018-01-19 | 2018-01-19
Domain
Service
Dto
getNextContestTime(IEnumerable<Contest>) | DataAccess | 1 | 2018-01-19 | 2018-01-19 | 1 | 2018-01-19 | 2018-01-19
Domain
Service
Dto
getContests(Acoording to filters) | DataAccess | 1 | 2018-01-19 | 2018-01-19 | 1 | 2018-01-19 | 2018-01-19 |  | We need to Add filter by Prizing Rule,
| Domain | [7 empty] | but we don't have defined the prizings yet
Service
Dto
getUserInfo(username) | DataAccess | 1 | 2018-01-19 | 2018-01-19 | 1 | 2018-01-19 | 2018-01-19
Domain
Service
Dto
getUsersBestRivals(actualUser, IEnumerable<User>, amount) | DataAccess | 1 | 2018-01-20 | 2018-01-20 | 1 | 2018-01-20 | 2018-01-20
Domain
Service
Dto
getUsersWorstRivals(actualUser, IEnumerable<User>, amount) | DataAccess | 1 | 2018-01-20 | 2018-01-20 | 1 | 2018-01-20 | 2018-01-20
Domain
Service
Dto
getUserFrieds(actualUser) | DataAccess | 1 | 2018-01-20 | 2018-01-20 | 1 | 2018-01-20 | 2018-01-20
Domain
Service
Dto
getLineups(actualUser) | DataAccess | 1 | 2018-01-21 | 2018-01-21 | 1 | 2018-01-21 | 2018-01-21
Domain
Service
Dto
getContest(Id) | DataAccess | 1 | 2018-01-22 | 2018-01-22 | 1 | 2018-01-22 | 2018-01-22
Domain
Service
Dto
getContests(Date) | DataAccess | 1 | 2018-01-22 | 2018-01-22 | 1 | 2018-01-22 | 2018-01-22
Domain
Service
Dto
getGamesFromContest(contestID) | DataAccess | 1 | 2018-01-22 | 2018-01-22 | 1 | 2018-01-22 | 2018-01-22
Domain
Service
Dto
getTeamsFromGames(IEnumerable<Game>) | DataAccess | 1 | 2018-01-23 | 2018-01-23 | 1 | 2018-01-23 | 2018-01-23
Domain
Service
Dto
getTeamsFromGame(GameID) | DataAccess | 1 | 2018-01-23 | 2018-01-23 | 1 | 2018-01-23 | 2018-01-23
Domain
Service
Dto
getPlayersFromTeam(TeamID) | DataAccess | 1 | 2018-01-24 | 2018-01-24 | 1 | 2018-01-24 | 2018-01-24
Domain
Service
Dto
getPlayersFromTeams(IEnumerable<Teams>) | DataAccess | 1 | 2018-01-24 | 2018-01-24 | 1 | 2018-01-24 | 2018-01-24
Domain
Service
Dto
putLineup(Lineup) | DataAccess | 1 | 2018-01-25 | 2018-01-25 | 1 | 2018-01-25 | 2018-01-25
Domain
Service
Dto
getLineups(actualUser) | DataAccess | 1 | 2018-01-25 | 2018-01-25 | 1 | 2018-01-25 | 2018-01-25
Domain
Service
Dto
getLineups(IdContest) | DataAccess | 1 | 2018-01-26 | 2018-01-26 | 1 | 2018-01-26 | 2018-01-26
Domain
Service
Dto
getGoals(ContestID) | DataAccess | 1 | 2018-01-26 | 2018-01-26 | 1 | 2018-01-26 | 2018-01-26
Domain
Service
Dto
getPlayer(ID) | DataAccess | 1 | 2018-01-27 | 2018-01-27 | 1 | 2018-01-27 | 2018-01-27
Domain
Service
Dto
getPlayers(lineupID) | DataAccess | 1 | 2018-01-27 | 2018-01-27 | 1 | 2018-01-27 | 2018-01-27
Domain
Service
Dto
getTeam(ID) | DataAccess | 1 | 2018-01-27 | 2018-01-27 | 1 | 2018-01-27 | 2018-01-27
Domain
Service
Dto
getNews(Team) | DataAccess | 1 | 2018-01-28 | 2018-01-28 | 1 | 2018-01-28 | 2018-01-28
Domain
Service
Dto
getNews(Player) | DataAccess | 1 | 2018-01-28 | 2018-01-28 | 1 | 2018-01-28 | 2018-01-28
Domain
Service
Dto
getGamesfromTeam(IdTeam) | DataAccess | 1 | 2018-01-29 | 2018-01-29 | 1 | 2018-01-29 | 2018-01-29
Domain
Service
Dto
getGame(IDGame) | DataAccess | 1 | 2018-01-29 | 2018-01-29 | 1 | 2018-01-29 | 2018-01-29
Domain
Service
Dto
putUser(userInfo) | Dto
Service
Domain
DataAccess
getTotalWinnings(actualUser) | DataAccess
Domain
Service
Dto
getWinLoseRecord(actualUser) | DataAccess
Domain
Service
Dto
getObtainedPoints(ContestID) | DataAccess
Domain
Subject to Prizing Definitions | Service
Dto
getUserEarnedCash(actualUser) | DataAccess
Domain
Subject to Prizing Definitions | Service
Dto

## Frontend Schedule
Página | Componentes | Time(Days) | Date |  | Completed
|  | Implentation | Start | End | (%)
Lobby | Contest Promotions | 10 | 2018-01-18 | 2018-01-28
| Active Contests | 10
| Notifications | TBD*
| Next Context Timer | 2
| Contest Filters | 3
| Menus | 2
Home | Promotions List
Notification List
Basic Site Information
Registration Form
Login form
My Account | User Info
Points
Money
Stats | Earned Cash
Graphics
Best Rivals (off Friends List)
Worst Rivals (off Friends List)
More To Be Determined
Friends | Friends List
Add Funds | Payment Platform Fields*
Notifications | Notification List
History | List of Lineups
Winnings (Total)
Record (W/L)
Help | Help Topics
Partake Contest | Contest Info
Games
Teams of The Games
Players of The Teams
Lineup
View Contest | Contest Info
Live Contest | Contest Info
Lineup
Competitors Lineup
Points/Goals
My Upcoming Contest | List of Contest ordered by lineup
Create Contest | Contest Gral Info
Prize Structure(Depend ^, ^^)
Player | Player Info
Game Stats (TBD)
Player Stats (TBD)
Recent Performance (TBD)
News (Related)
Team | Team Info
News (Related)
Upcoming Games
Game | Game Info
Lineup | List of Players