## General Schedule
Página | Componentes | Funcion Especifica de Consulta | Time (Days) |  | Requirements
|  |  | FrontEnd | BackEnd
Lobby | Contest Promotions | getContests | 10 | 0 | Already Done
| Active Contests | getPromotions | 10 | 2
| Informations | getInformations/getInformations(StartDate,EndDate) | TBD* | 1
| Next Context Timer | getNextContestTime(IEnumerable<Contest>) | 2 | 2
| Contest Filters | getContests(Acoording to filters) | 3 | 1
| Menus |  | 2 | 0
Home | Promotions List | getPromotions | TBD* | 0 | Backend Already Done for the Lobby Page
| Notification List | getNotifications |  | 1
| Basic Site Information | TBD |  | TBD | * when desing is finished
Registration Form |  | putUser(userInfo) | TBD* | 7 | * when desing is finished - fe time extended to study REST
Login form |  |  | TBD* | 3 | * when desing is finished
My Account | User Info | getUserInfo(username) | TDB* | 0.5 | * when desing is finished
Points
Money
Stats | Earned Cash | getUserEarnedCash(actualUser) | TBD* | 0.5 | * when desing is finished - fe time subject to definition of prizing
| Graphics | TBD |  | TBD
| Best Rivals (off Friends List) | getUsersBestRivals(actualUser, IEnumerable<User>, amount) |  | 0.5
| Worst Rivals (off Friends List) | getUsersWorstRivals(actualUser, IEnumerable<User>, amount) |  | 0.5
| More To Be Determined | TBD |  | TBD
Friends | Friends List | getUserFrieds(actualUser) | TBD* | 3
Add Funds | Payment Platform Fields* | TBD | TBD* | TBD
Notifications | Notification List | getNotifications | TBD* | 0 | * when desing is finished -- Already done in Lobby
History | List of Lineups | getLineups(actualUser) | TBD* | 5 | * when desing is finished
| Winnings (Total) | getTotalWinnings(actualUser) |  | 5
| Record (W/L) | getWinLoseRecord(actualUser) |  | 2
Help | Help Topics | TDB | TBD* | TBD | We need to discuss help topics and how to show them - * when desing is finished
Partake Contest | Contest Info | getContest(Id) | 1 | 2
| Games | getGamesFromContest(contestID) | 1 | 2
| Teams of The Games | getTeamsFromGames(IEnumerable<Game>) | 3 | 0 | Uses getTeamsFromGame
|  | getTeamsFromGame(GameID) |  | 2
| Players of The Teams | getPlayersFromTeam(TeamID) | 3 | 0 | Already done
|  | getPlayersFromTeams(IEnumerable<Teams>) |  | 1 | Uses getPlayersFromTeam
| Lineup | putLineup(Lineup) | 5 | 10 | Requires to study a bit of REST and to test the saving modality on the db
View Contest | Contest Info | getContest(Id) | 7 | 0 | Defined in Partake Contests
Live Contest | Contest Info | getContest(Id) | 1 | 0 | Defined in Partake Contests
| Lineup | getLineups(actualUser) | 1 | 2
| Competitors Lineup | getLineups(IdContest) | 1 | 2
| Points/Goals | getGoals(ContestID) | 2 | 5
|  | getObtainedPoints(ContestID) | 3 | 5
My Upcoming Contest | List of Contest ordered by lineup | getContests(Date) | TBD* | 2
Create Contest | Contest Gral Info | getContest(Id) | TBD* | 0 | Defined in Partake Contests
| Prize Structure(Depend ^, ^^) | TBD |  | TBD | funtions That depend on the Contest Type and Entry Fee TBD
Player | Player Info | getPlayer(ID) | TBD* | 2
| Game Stats (TBD) | TBD |  | TBD
| Player Stats (TBD) | TBD
| Recent Performance (TBD) | TBD
| News (Related) | getNews(Player) |  | 3
Team | Team Info | getTeam(ID) | TBD* | 2
| News (Related) | getNews(Team) |  | 2
| Upcoming Games | getGamesfromTeam(IdTeam) |  | 2
Game | Game Info | getGame(IDGame) | TBD* | 2
Lineup | List of Players | getPlayers(lineupID) | TBD* | 2
|  | Weeks in Case of Implementation Errors | 4 | 4
|  | Days | 59 | 86
|  | Weeks | 8.4286 | 12.2857

## Backend Schedule
Task No. | Function | API Layer Implementation | Time(Days) | Date |  | Time(Days) | Date |  | Completed | Status
|  |  | Implentation | Start | End | Testing | Start | End | (%)
1 | getContests | DataAccess | [6 empty] | 100%
2 |  | Domain
3 |  | Service
4 |  | Dto
5 | getActiveContests | DataAccess | 0.1 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
6 |  | Domain | 0.1 | 2018-01-26 | 2018-01-26 | 0.1 | 2018-01-26 | 2018-01-26
7 |  | Service | 0.13 | 2018-06-02 | 2018-06-02 | 0.13 | 2018-06-02 | 2018-06-02
8 |  | Dto | 0.13 | 2018-06-02 | 2018-06-02 | 0.13 | 2018-06-02 | 2018-06-02
9 | getActiveNotifications | DataAccess | 0.13 | 2018-01-18 | 2017-01-18 | 0.13 | 2018-01-18 | 2018-01-18 | 100%
10 |  | Domain | 0.1 | 2018-01-26 | 2018-01-26 | 0.1 | 2018-01-26 | 2018-01-26
11 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
12 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
13 | getUserActiveNotifications(user) | DataAccess | 0.13 | 2018-01-18 | 2017-01-18 | 0.13 | 2018-01-18 | 2018-01-18 | 100%
14 |  | Domain | 0.13 | 2018-01-27 | 2018-01-27 | 0.13 | 2018-01-27 | 2018-01-27
15 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
16 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
17 | getInformations | DataAccess | 0.13 | 2018-01-18 | 2017-01-18 | 0.13 | 2018-01-18 | 2018-01-18 | 100%
18 |  | Domain | 0.13 | 2018-01-27 | 2018-01-27 | 0.13 | 2018-01-27 | 2018-01-27
19 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
20 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
21 | getInformations(Start Date, End Date) | DataAccess | 0.13 | 2018-01-18 | 2017-01-18 | 0.13 | 2018-01-18 | 2018-01-18 | 100%
22 |  | Domain | 0.13 | 2018-01-27 | 2018-01-27 | 0.13 | 2018-01-27 | 2018-01-27
23 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
24 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
25 | getPromotions | DataAccess | 0.25 | 2018-01-19 | 2018-01-19 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
26 |  | Domain | 0.13 | 2018-01-27 | 2018-01-27 | 0.13 | 2018-01-27 | 2018-01-27
27 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
28 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
29 | getNextContestTime(IEnumerable<Contest>) | DataAccess | 0.25 | 2018-01-19 | 2018-01-19 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
30 |  | Domain | 0.13 | 2018-01-28 | 2018-01-28 | 0.13 | 2018-01-28 | 2018-01-28
31 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
32 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
33 | getContests(Acoording to filters) | DataAccess | 0.25 | 2018-01-19 | 2018-01-19 | 0.04 | 2018-01-21 | 2018-01-21 | 100% |  | We need to Add filter by Prizing Rule,
34 |  | Domain | 0.13 | 2018-01-28 | 2018-01-28 | 0.13 | 2018-01-28 | 2018-01-28 |  |  | but we don't have defined the prizings yet
35 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
36 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
37 | getUserInfo(username) | DataAccess | 0.25 | 2018-01-19 | 2018-01-19 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
38 |  | Domain | 0.13 | 2018-01-28 | 2018-01-28 | 0.13 | 2018-01-28 | 2018-01-28
39 |  | Service | 0.1 | 2018-01-28 | 2018-01-28 |  | 2018-01-28 | 2018-01-28
40 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
41 | getUsersBestRivals(actualUser, IEnumerable<User>, amount) | DataAccess | 0.33 | 2018-01-20 | 2018-01-20 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
42 |  | Domain | 0.13 | 2018-01-28 | 2018-01-28 | 0.13 | 2018-01-28 | 2018-01-28
43 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
44 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
45 | getUsersWorstRivals(actualUser, IEnumerable<User>, amount) | DataAccess | 0.33 | 2018-01-20 | 2018-01-20 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
46 |  | Domain | 0.1 | 2018-01-29 | 2018-01-29 | 0.1 | 2018-01-29 | 2018-01-29
47 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
48 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
49 | getUserFrieds(actualUser) | DataAccess | 0.33 | 2018-01-20 | 2018-01-20 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
50 |  | Domain | 0.1 | 2018-01-29 | 2018-01-29 | 0.1 | 2018-01-29 | 2018-01-29
51 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
52 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
53 | getLineups(actualUser) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
54 |  | Domain | 0.1 | 2018-01-29 | 2018-01-29 | 0.1 | 2018-01-29 | 2018-01-29
55 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
56 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
57 | getActiveLineups(actualUser) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
58 |  | Domain | 0.13 | 2018-01-29 | 2018-01-29 | 0.13 | 2018-01-29 | 2018-01-29
59 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
60 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
61 | getContest(Id) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
62 |  | Domain | 0.1 | 2018-01-29 | 2018-01-29 | 0.1 | 2018-01-29 | 2018-01-29
63 |  | Service | 0.13 | 2018-02-27 | 2018-06-02 | 0.13 | 2018-02-27 | 2018-06-02
64 |  | Dto | 0.13 | 2018-02-27 | 2018-06-02 | 0.13 | 2018-02-27 | 2018-06-02
65 | getContests(Date) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
66 |  | Domain | 0.1 | 2018-01-29 | 2018-01-29 | 0.1 | 2018-01-29 | 2018-01-29
67 |  | Service | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
68 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
69 | getGamesFromContest(contestID) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
70 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
71 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
72 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
73 | getTeamsFromGames(IEnumerable<Game>) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
74 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
75 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
76 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
77 | getTeamsFromGame(GameID) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
78 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
79 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
80 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
81 | getPlayersFromTeam(TeamID) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
82 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
83 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
84 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
85 | getPlayersFromTeams(IEnumerable<Teams>) | DataAccess | 0.04 | 2018-01-21 | 2018-01-21 | 0.04 | 2018-01-21 | 2018-01-21 | 100%
86 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
87 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
88 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
89 | getLineups(IdContest) | DataAccess | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31 | 100%
90 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
91 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
92 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
93 | getGoals(ContestID) | DataAccess | 0.2 | 2018-01-23 | 2018-01-23 | 0.2 | 2018-01-23 | 2018-01-23 | 100%
94 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
95 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
96 |  | Dto | 0.1 | 2018-02-28 | 2018-02-28 | 0.1 | 2018-02-28 | 2018-02-28
97 | getPlayer(ID) | DataAccess | 0.2 | 2018-01-23 | 2018-01-23 | 0.2 | 2018-01-23 | 2018-01-23 | 100%
98 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
99 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
100 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
101 | getPlayers(lineupID) | DataAccess | 0.25 | 2018-01-24 | 2018-01-24 | 0.25 | 2018-01-24 | 2018-01-24 | 100%
102 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
103 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
104 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
105 | getTeam(Id) | DataAccess | 0.25 | 2018-01-24 | 2018-01-24 | 0.25 | 2018-01-24 | 2018-01-24 | 100%
106 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
107 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
108 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
109 | getGamesfromTeam(IdTeam) | DataAccess | 0.25 | 2018-01-25 | 2018-01-25 | 0.25 | 2018-01-25 | 2018-01-25 | 100%
110 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
111 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
112 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
113 | getGame(IDGame) | DataAccess | 0.25 | 2018-01-25 | 2018-01-25 | 0.25 | 2018-01-25 | 2018-01-25 | 100%
114 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
115 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
116 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
117 | getNews(Dates) | DataAccess | 0.1 | 2018-01-26 | 2018-01-26 | 0.1 | 2018-01-26 | 2018-01-26 | 100%
118 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
119 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
120 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
121 | getNews(Team) | DataAccess | 0.1 | 2018-01-26 | 2018-01-26 | 0.1 | 2018-01-26 | 2018-01-26 | 100%
122 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
123 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
124 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
125 | getNews(Player) | DataAccess | 0.1 | 2018-01-26 | 2018-01-26 | 0.1 | 2018-01-26 | 2018-01-26 | 100%
126 |  | Domain | 0.1 | 2018-01-31 | 2018-01-31 | 0.1 | 2018-01-31 | 2018-01-31
127 |  | Service | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
128 |  | Dto | 0.1 | 2018-01-03 | 2018-01-03 | 0.1 | 2018-01-03 | 2018-01-03
129 | getTotalWinnings(actualUser) | DataAccess | [8 empty] | This depends upon the definition of Prizing Sructures
130 |  | Domain
131 |  | Service
132 |  | Dto
133 | getWinLoseRecord(actualUser) | DataAccess | [8 empty] | This depends upon the definition of Prizing Sructures
134 |  | Domain
135 |  | Service
136 |  | Dto
137 | getObtainedPoints(ContestID) | DataAccess
138 |  | Domain
139 | Subject to Prizing Definitions | Service
140 |  | Dto
141 | getUserEarnedCash(actualUser) | DataAccess | [8 empty] | This depends upon the definition of Prizing Sructures
142 |  | Domain
143 | Subject to Prizing Definitions | Service
144 |  | Dto
145 | getSport(id) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
146 |  | Domain
147 |  | Service
148 |  | Dto
149 | getPosition(id) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-14 | 2018-03-14
150 |  | Domain
151 |  | Service
152 |  | Dto
153 | getClimaCondition(id) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
154 |  | Domain
155 |  | Service
156 |  | Dto
157 | getContestType(id) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
158 |  | Domain
159 |  | Service
160 |  | Dto
161 | getVenue(id) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
162 |  | Domain
163 |  | Service
164 |  | Dto
165 | postInformation(info) | DataAccess | 1 | 2018-03-13 | 2018-03-13 | 0.5 | 2018-03-13 | 2018-03-14
166 |  | Domain
167 |  | Service
168 |  | Dto
169 | putInformation(Info) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
170 |  | Domain
171 |  | Service
172 |  | Dto
173 | deleteInformation(Info) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
174 |  | Domain
175 |  | Service
176 |  | Dto
177 | postPromotion(Promo) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
178 |  | Domain
179 |  | Service
180 |  | Dto
181 | putPromotion(Promo) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
182 |  | Domain
183 |  | Service
184 |  | Dto
185 | deletePromotion(Promo) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
186 |  | Domain
187 |  | Service
188 |  | Dto
189 | postContestType(Promo) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
190 |  | Domain
191 |  | Service
192 |  | Dto
193 | putContestType(Promo) | DataAccess
194 |  | Domain
195 |  | Service
196 |  | Dto
197 | deleteContestType(Promo) | DataAccess
198 |  | Domain
199 |  | Service
200 |  | Dto
201 | postSport(Sport) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
202 |  | Domain
203 |  | Service
204 |  | Dto
205 | putSport(Sport) | DataAccess
206 |  | Domain
207 |  | Service
208 |  | Dto
209 | deleteSport(Sport) | DataAccess
210 |  | Domain
211 |  | Service
212 |  | Dto
213 | postPosition(Position) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
214 |  | Domain
215 |  | Service
216 |  | Dto
217 | putPosition(Position) | DataAccess
218 |  | Domain
219 |  | Service
220 |  | Dto
221 | deteltePosition(Position) | DataAccess
222 |  | Domain
223 |  | Service
224 |  | Dto
225 | postClimaCondition(ccondition) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
226 |  | Domain
227 |  | Service
228 |  | Dto
229 | putClimaCondition(ccond) | DataAccess
230 |  | Domain
231 |  | Service
232 |  | Dto
233 | detelteClimaCondition(ccond) | DataAccess
234 |  | Domain
235 |  | Service
236 |  | Dto
237 | postVenue(Venue) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
238 |  | Domain
239 |  | Service
240 |  | Dto
241 | putVenue(Venue) | DataAccess
242 |  | Domain
243 |  | Service
244 |  | Dto
245 | detelteVenue(Venue) | DataAccess
246 |  | Domain
247 |  | Service
248 |  | Dto
249 | postNotification(Notification) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
250 |  | Domain
251 |  | Service
252 |  | Dto
253 | putNotification(Notification) | DataAccess
254 |  | Domain
255 |  | Service
256 |  | Dto
257 | detelteNotification(Notification) | DataAccess
258 |  | Domain
259 |  | Service
260 |  | Dto
261 | postGoal(Goal) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
262 |  | Domain
263 |  | Service
264 |  | Dto
265 | putGoal(Goal) | DataAccess
266 |  | Domain
267 |  | Service
268 |  | Dto
269 | detelteGoal(Goal) | DataAccess
270 |  | Domain
271 |  | Service
272 |  | Dto
273 | postTeam(Team) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
274 |  | Domain
275 |  | Service
276 |  | Dto
277 | putTeam(Team) | DataAccess
278 |  | Domain
279 |  | Service
280 |  | Dto
281 | detelteTeam(Team) | DataAccess
282 |  | Domain
283 |  | Service
284 |  | Dto
285 | postNews(News) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
286 |  | Domain
287 |  | Service
288 |  | Dto
289 | putNews(News) | DataAccess
290 |  | Domain
291 |  | Service
292 |  | Dto
293 | detelteNews(NEws) | DataAccess
294 |  | Domain
295 |  | Service
296 |  | Dto
297 | postLeague(League) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
298 |  | Domain
299 |  | Service
300 |  | Dto
301 | putLeague(League) | DataAccess
302 |  | Domain
303 |  | Service
304 |  | Dto
305 | detelteLeague(League) | DataAccess
306 |  | Domain
307 |  | Service
308 |  | Dto
309 | postInjury(Injury) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
310 |  | Domain
311 |  | Service
312 |  | Dto
313 | putInjury(Injury) | DataAccess
314 |  | Domain
315 |  | Service
316 |  | Dto
317 | detelteInjury(Injury) | DataAccess
318 |  | Domain
319 |  | Service
320 |  | Dto
321 | postLineUp(Injury) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
322 |  | Domain
323 |  | Service
324 |  | Dto
325 | putLineUp(LineUp) | DataAccess
326 |  | Domain
327 |  | Service
328 |  | Dto
329 | detelteLineUp(LineUp) | DataAccess
330 |  | Domain
331 |  | Service
332 |  | Dto
333 | postAccount(USer) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
334 |  | Domain
335 |  | Service
336 |  | Dto
337 | putAccount(Account) | DataAccess
338 |  | Domain
339 |  | Service
340 |  | Dto
341 | detelteAccount(Account) | DataAccess
342 |  | Domain
343 |  | Service
344 |  | Dto
345 | postPlayer(Player) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
346 |  | Domain
347 |  | Service
348 |  | Dto
349 | putPlayer(Player) | DataAccess
350 |  | Domain
351 |  | Service
352 |  | Dto
353 | deteltePlayer(Player) | DataAccess
354 |  | Domain
355 |  | Service
356 |  | Dto
357 | postGame(Game) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
358 |  | Domain
359 |  | Service
360 |  | Dto
361 | putGame(Game) | DataAccess
362 |  | Domain
363 |  | Service
364 |  | Dto
365 | detelteGame(Game) | DataAccess
366 |  | Domain
367 |  | Service
368 |  | Dto
369 | postContest(Contest) | DataAccess | 0.1 | 2018-03-14 | 2018-03-14 | 0.1 | 2018-03-15 | 2018-03-15
370 |  | Domain
371 |  | Service
372 |  | Dto
373 | putContest(Contest) | DataAccess
374 |  | Domain
375 |  | Service
376 |  | Dto
377 | detelteContest(Contest) | DataAccess
378 |  | Domain
379 |  | Service
380 |  | Dto
|  |  | 18.06 |  |  | 15.69
| Total | 33.75

## Frontend Schedule
Página | Componentes | Time(Days) | Date |  | Completed
|  | Implentation | Start | End | (%)
Lobby | Contest Promotions | 10 | 2018-01-18 | 2018-01-28
| Active Contests | 10
| Notifications | TBD*
| Next Context Timer | 2
| Contest Filters | 3
| Menus | 2
Home | Promotions List
Notification List
Basic Site Information
Registration Form
Login form
My Account | User Info
Points
Money
Stats | Earned Cash
Graphics
Best Rivals (off Friends List)
Worst Rivals (off Friends List)
More To Be Determined
Friends | Friends List
Add Funds | Payment Platform Fields*
Notifications | Notification List
History | List of Lineups
Winnings (Total)
Record (W/L)
Help | Help Topics
Partake Contest | Contest Info
Games
Teams of The Games
Players of The Teams
Lineup
View Contest | Contest Info
Live Contest | Contest Info
Lineup
Competitors Lineup
Points/Goals
My Upcoming Contest | List of Contest ordered by lineup
Create Contest | Contest Gral Info
Prize Structure(Depend ^, ^^)
Player | Player Info
Game Stats (TBD)
Player Stats (TBD)
Recent Performance (TBD)
News (Related)
Team | Team Info
News (Related)
Upcoming Games
Game | Game Info
Lineup | List of Players